## Product Backlog
Group – 7: Abhishek Nalawade, Aditya Jadhav
Human Obstacle Detector
Product Backlog

					Completed
					In Progress
					To Do
					Failed

Sprint	Task ID	Task Description	Estimated Time (Minutes)	Time for Iteration 1 (Minutes)	Time for Iteration 2 (Minutes)	Status	Comments
Design		Planning and designing the project in phases	1195	390	0
1	1	Create GitHub Repository	10	10	0
	2	Create Project Proposal	320	380	0
	3	Extensive Research on HOG, SVM and technology required	360	0	0
	4	Install Dependencies	150	0	0
	5	Acquire Travis and Coveralls badges	15	0	0
	6	Add .travis.yml file with dependencies	20	0	0
	7	Add detailed Readme.md	60	0	0
	8	Create CmakeLists.txt file	20	0	0
	9	Write Stubs for classes	120	0	0
	10	Write Tests for the stubs	60	0	0
	11	Run Cpplint and Cppcheck	30	0	0
	12	Generate Doxygen documentation	30	0	0

Sprint	Task ID	Task Description	Estimated Time (Minutes)	Time for Iteration 1 (Minutes)	Time for Iteration 2 (Minutes)	Status	Comments
Implementation		Implementation and Optimization of the design	1680	0	0
2	1	Rework Class and Activity diagrams	100	0	0
	2	Implement Data class and write for it	200	0	0
	3	Implement Train class and write for it	220	0	0
	4	Implement Detect class and write for it	240	0	0
	5	Implement Distance class and write for it	200	0	0
	6	Load Training data and train classifier	150	0	0
	7	Tune weights of the model	150	0	0
	8	Update all tests accordingly to increase coverage	120	0	0
	9	Re-run Cpplint and Cppcheck	90	0	0
	10	Update Class, Activity diagrams and Readme.md	90	0	0
	11	Fill Work log	60	0	0
	12	Update Doxygen documentation and results folder	60	0	0

		Total Effort Time	2875	390	0